## Cover Sheet
Capstone Consulting Services - Inventory
Risk Log
Version 1.0
Project Executive: Andrew Williams
Daily Contact: Preston Gates
Project Manager: Garrett Keylor
Team Members: Kalia Antoniou, Cole Hamblin, Braden Carlson

## Risk Log
Risk Log
Risk ID | Risk Category | Business Area | Risk Description | Impact (1-5) | Probability (0-1) | Date Logged | Risk Handling Approach | Mitigation Strategy | Contingency Plan | Resolution | Risk Realized Y/N | Status | Owner | Date Risk Will Have Expired | Next Review Date | Comments/Follow-Up Activity
1 | Time | Solution | The teams currently do not process sufficient time to finish the project | 5 | 25% | 2021-02-12 | Mitigate risk by splitting up work more efficiently between the team and effectively using team members. Incourage open communication with other memebers and coach. | Project manager works with team to ensure that work is completed within the timeline. Proper delegation of tasks. | Make sure to document frequently. Focus only on the high priorty requirements to satisfy the client's needs. Then look to add lower level priority features. |  | N | New | Garrett Keylor | 2021-04-23
2 | Infrastructure | Solution | The team has problems connecting the back-end/front-end applications together | 5 | 30% | 2021-02-12 | Mitigate risk by testing frequently and work efficiently to have enough time to debug and solve unforseen problems. | Frequent updates of project stability and problems. Open communication between team memebers, contact, and coach. | Take full advantage of office hours and coach's knowledge. Conduct proper research. Inform coach and contact of any problems we have when they arise. |  | N | New | Garrett Keylor | 2021-04-23
3 | Infrastructure | Solution | Database has issues connecting to the front/back-end application and properly storing data | 5 | 25% | 2021-02-12 | Mitigate risk by testing any changes when code is updated. Contact coach and contact on proper ways to set up the database. | Contacting coach and contact. Proper research of previous implementations and problems others have had. | Take full advantage of office hours and coach's knowledge. Conduct proper research. Inform coach and contact of any problems we have when they arise. |  | N | New | Garrett Keylor | 2021-04-23
4 | Team | Solution | Team members are unavailable to work on the project due to illness, or other responsibiliteis | 3 | 45% | 2021-02-12 | Mitigate risk by making sure we are on schedule for stage gates and giving timely updates. Open communication is a must | Consistent communication with updates on our status. Especially communication prior to known conflicts. | Focus on the high priority tasks and divide those accordingly |  | N | New | Garrett Keylor | 2021-04-23
5 | Communication | Solution | Team memebers do not communicate cleary and do not indetify problems. | 3 | 25% | 2021-02-15 | Mitigate risk by communicating frequenlty and provide updates if we are having trouble with a specific problem or implementation | Team memebers should have clear direction on what part of the project they are working on. Harder issues and problems should be worked on collaboratively. | Proper team member assignment to problems and with open communication |  | N | New | Garrett Keylor | 2021-04-23
6 | Code Updates | Solution | Improper updates of code that could cause unforseen problems. | 3 | 35% | 2021-02-16 | Mitigate risk by using proper software control to handle updates | Use software (Git) to properly stage changes and revert if necessary | Teams will use version tracking and stage changes to return code to previous state and correct unforseen issues |  | N | New | Garrett Keylor | 2021-04-23
7 | Scope | Solution | Controlling scope of project and feature creep | 4 | 50% | 2021-02-16 | Mitigate risk by talking to Executive and understanding priority of features. Communication between team members to make sure all members are on track and working on the right features | Frequently assess project and move non-critical features to backlog | Use the weekly updates with Preston to make sure we are on the right track. Each week we have team updates to understand priority of upcoming features. |  | N | New | Garrett Keylor | 2021-04-23
8 | Testing Environment | Solution | Unforseen bugs in code that require additional time to correct | 2 | 80% | 2021-02-16 | Mitigate risk by using proper naming conventions, test / plan log, and using Desing Patterns, and testing frequently | Inform contact in weekly updates about bugs before they become a big issue. Test code frequenlty. | Inform Preston of bugs when they arise, revert changes if necessary |  | N | New | Garrett Keylor | 2021-04-23

## Issues Log
Issues Log
Issue ID | Risk Category | Business Area | Issue Description | Impact (1-5) | Probability (0-1) | Exposure (0 - 5) | Date Logged | Issue Handling Approach | Mitigation Strategy | Contingency Plan | Resolution | Status | Owner | Date Risk Will Have Expired | Next Review Date | Comments/Follow-Up Activity
1
2
3
4
5
6
7
8

## Revision History
Revision History
| Date | Version | Description | Author
| 2020-02-10 | 1 | Initial Draft | Garrett Keylor